## Slide 1
National Catering Production Strategy.
Derek Cullen
National Programme Director Catering

## Slide 2
National Catering Strategy
CASE FOR CHANGE
CENTRALISED PRODUCTION FACILITIES X 4
PHASED APPROACH
NHS LOTHIAN / EAST REGION CPU
SERVICE MODEL
Procurement Cook Freeze Production Hospital Ward Patient
How much will this cost?
What are the risks?
What are the dependencies?
What are the benefits?
How will it be delivered?
What about the workforce?
OUTCOMES
Consistency
High quality (e.g. nutritious /compliant)
Safe
Skilled staff
Efficient i.e. cost and productivity
Continuous service delivery
PARAMETERS
NHS Operated
For NHS (initially)
Cook freeze
Collaborative working across populations
National Information System
National Recipe Database
Standard Operating Procedures replicated nationwide
National Training
National R&D
Sustainable

## Slide 3
Programme Status
Programme / Project milestones
Milestone | Planned Completion Date | Actual Completion Date | % Completed | RAG
NCIS Tender award | Sep-18 |  | 50 | 
NCIS Implementation to early adopter Boards | Mar-19 |  | 0 | 
National Recipe Database | Oct-18 |  | 50 | 
Development of IA for East Region Central Production Unit | Sept/Oct 2018 |  | 60 | 
Development and implementation of Retail Strategy | Mar-19 |  | 0 | 
Development of Standard Operating Procedures | Dec-18 |  | 10 | 
Food waste reduction by 300k | Mar-19 |  | 0 | 
Retail subsidy reduction by 200k | Mar-19 |  | 0 | 
Regional Catering Strategy Development and implementation | Mar-19 |  | 10 | 
Porter Track trials | Mar-19 |  | 0 | 

## Slide 4
Financial Benefits Realisation
  NCIS
  Food waste (ref 17/18 Q3 Benchmarking)
  Total projected food expenditure for 17/18 = £23,000,344
  Total projected food waste =£1,624,824 (7%)
  6 NHS Boards account for 90% of total food waste
  Same 6 NHS Boards also account for 80% of annual food expenditure
  Planned Action
  Support these Boards to achieve reductions in 18/19
  Propose these Boards as early adopters of NCIS from Autumn 2018
  Benefits realisation
  2019/20 – minimum £326,000 up to potential £1.1m recurring gained by better food purchasing and ward ordering

## Slide 5
Financial Benefits Realisation
  Non Patient Catering (Retail)
  Trading account 2016/17 = £1,001,355 deficit
  5 NHS Boards account for combined deficit =£1.3m
  Anticipate improvement for 17/18 based upon recent feedback from some Boards
  Planned Action Benefits
  Apply 2.5% increases as per CE ASSP from April 2018 across all Boards
  Develop and implement a Retail Strategy including appointment Retail Support Manager by October 2018
  Develop Retail Expert Group by June 2018
  Support the 5 NHS Boards through engagement from April 2018. If these Boards were to achieve a 30% reduction in subsidy (as per NHS Fife 17/18 projection) the savings would be around 400k in 18/19.

## Slide 6
Thank you
Derek Cullen
National Programme Director Catering
derek.cullen@nhs.net
Telephone: 0777 941 9386